## Slide 1
Ms. Vandana Gurnani
Joint Secretary (Reproductive and Child Health)
Ministry of Health & Family Welfare
Government of India
India-Country Experience - Measles Rubella Vaccination

## Slide 2: Political Will & Ownership
Government commitment to eliminate measles and control rubella by 2020
PM Narendra Modi in government advert to promote Measles Rubella vaccination campaign
Arun Jaitley, Finance Minister’s speech, 2017-2018

## Slide 3: Measles Rubella Campaign Phase – 1
Country Preparedness

## Slide 4: Measles-Rubella Vaccine Introduction in the Country
NTAGI in 2014 recommended introduction of rubella vaccine as Measles-Rubella (MR) vaccine through a wide age range campaign (9 months to 15 years)
Gavi supporting about 45% of target cohort MR vaccine requirement for the campaign.
Phase 1
Phase 2
COMPLETED BY FEB 17: ~35 mn
  ONGOING AUG - SEPT 17: ~35 mn
  PLANNED FEB - OCT 18: ~336 mn
Phase 5
Phase 3
Phase 4
Vaccine introduction in routine immunization, in replacement of 2 doses of measles.
>400 million children targeted
(9 months to < 15 yrs)
Notes: Measles Rubella Campaign Phase – 1 was started in February 2017 in 5 States/UTs ( Goa, Lakshadweep, Karnataka, Tamil Nadu and Puducherry)
Phase 2 from August in 8 States/UTs. 6 States has started: Andhra, Telangana, Himachal, Chandigarh, Daman and Diu , Dadra and Nagar Haveli
Phase 3: planned in first quarter 2018, 11 states /UTs (8 NE states, WB , Odisha, Andaman )
Phase 4 planned in Bihar, Rajasthan and MP
Phase 5 in Gujarat, UP, Haryana, Jharkhand

## Slide 5: SIA*: Phase 1 (Feb/March 2017) – Institutional Mechanism
National Level Oversight
National Measles-Rubella Task Force
Measles-Rubella Operations group
Measles-Rubella Communications group
India Expert Advisory Group on Measles & Rubella (IEAG-MR)
Inter-Ministerial Committee
State level
  State Steering Committee
  State Operations Group
  State Task Force on Immunization
State Level Overview
District level
  District Task Force on Immunization
  District Immunization Officer’ review
PHASE 1 : COVERAGE OF 5 STATES
Goa, Tamil Nadu, Puducherry, Karnataka, Lakshwadeep islands
*Supplementary Immunization Activity
Notes: Institutional mechanism of supervision and monitoring was established at all levels in coordination with all stakeholders to make the implementation smooth
National Measles-Rubella Task Force Chaired by Joint Secretary, Govt. of India
  Members from WHO, UNICEF, BMGF, ICMR, National CDC
  Monitors and reviews campaign planning & surveillance data; national action plan development for measles elimination & rubella/CRS control
Measles-Rubella Operations group members include WHO, UNICEF, BMGF and ITSU
  Phasing plan, strengthening operational strategies following learnings from phase 1
Measles-Rubella Communications group
  members include WHO, UNICEF, BMGF, GHS
  Communication plan, media package, developing special strategies following learnings from phase 1
IEAG for MR members include national and international experts to provide technical strategic guidance for Measles elimination and Rubella control
Secretary, H& FW is the chair

## Slide 6: MR Vaccine Campaign: Implementation Strategy
Implementation of Session Sites
Fixed in-facility sites Hospitals, CHCs, PHCs, SC
Outreach session sites Villages, resettlement areas (one village, one day)
Mobile sessions For far flung areas
Continuous sessions in some facilities with high vaccination load to function throughout campaign period.
Schools
Community
Last week sweeping in low performing areas
4 weeks activity
1 week sweeping
Notes: Total duration of campaign 4 weeks (first in schools and then in community) and 1 week sweeping activity in low performing areas
Vaccination will be provided at: schools, health facilities and routine immunization session sites. Migratory sites to be approached through mobile teams
Regular RI sessions will be conducted as per usual planning

## Slide 7: Preparedness Assessment and deployment of monitors
The preparedness assessment by national monitors led to improvement before start of campaign, e.g.
Improved accountability
Sensitization of Education Dept.
Engagement of schools
Communication plans
Injection safety
AEFI management system
WHO-NPSP and UNICEF supported in monitoring training, advocacy and capacity building
Additional SMO/ RRTs (Rapid Response Teams) from other states deployed
Both session site and community were monitored

## Slide 8: State Planning workshop and TOT
State Nodal Officers Orientation Meeting
Cascaded Trainings and micro-planning:
  At all levels including stakeholders like Education Dept., WCD dept., Media, Schools etc.
Medical Officers orientation in AEFI management
Capacity building and trainings for MR campaign
Notes: State level workshops in all states
69 district level training workshops were conducted to sensitize key health and other department officials
Further trainings done at sub-district levels

## Slide 9: Measles-Rubella Campaign Launch
Campaign launched on 5th February, 2017 at Bangalore, Karnataka
Highest level political involvement at the launch

## Slide 10: Campaign Challenges
Rumors, misconceptions and inaccurate information disseminated through social media affected the campaign at the early stage
Other media platforms such as print and electronic media, opinions of leaders also played a role to some extent
  Inaccurate reports of AEFI cases, wrong information about vaccines had a negative impact
Sub-optimal participation of school Principals
Varied involvement of pediatric associations

## Slide 11: Addressing the Challenges (National, State and District Level)
Strong IEC approach - Appeals from Chief Minster & Health Minister published in 41 newspapers in different languages
FAQs put up on MoHFW website, WHO website
  Health Minister’s Appeal to Doctors
  Letter from Chief Secretary to DCs
  District level sensitization of Education and WCD Dept.
  Letter from religious Waqf Board and Urdu Appeals
Stakeholder orientation
  Parents, Teachers and Head masters meeting by District Collectors and Medical Officers
  Pediatric association presence in all advocacy meetings
Inter-ministerial support for MR campaign
  For eg. Ministry of HRD followed-up for issue of letters to schools

## Slide 12: Addressing the Challenges (Contd.)
Convergence Meetings with all key stakeholders at both district and sub-district level
Media Engagement
  Opinion articles, stakeholder interviews on national, local media including vernacular language to dispel the myths
  Awareness programs in Radio and TV
  Panel discussions and live phone in programs
  Warnings through visual and print media
  All India Radio (AIR) jingles
  A-V clips of experts, pediatricians, opinion leaders circulated on social media
Awareness campaigns
District Collector getting his child vaccinated on the day-1 of MR Campaign- Thiruvarur, TN

## Slide 13: Addressing the Challenges (Contd.)
Polio SIAs rescheduled in some states for focus on MR campaign activities
Extension of MR activity to allow more time to states to achieve the target
Campaign coverage review and feedback shared with States/UTs
Notes: Daily coverage is reviewed at national level and feedback shared with states. On the basis of performance, states were asked to take corrective actions to increase the coverage, involve schools and stakeholders . Also states were asked to increase the duration of campaign to achieve the desired coverage.

## Slide 14: Learnings from the 1st phase
Addressing critical FAQs such as the need of an additional dose and vaccine safety (sterility of vaccines, imported vaccines)
National Polio Surveillance Project (NSPS) support at field level critical in achieving good coverage in campaign
Potential for negative influence through social media and chat platforms (e.g. WhatsApp)
Resistance from minority communities
Scope of improvement of coordination with education department /private sector/pediatricians/clinicians
Variable preparation of communication plans
Need for brand ambassador/ champion for MR campaign
Need for effective media engagement
Notes: Challenges during phase-1 were identified
WHO-SMO support at field level critical in achieving good coverage in MR campaign
Need for a special strategy for schools
involvement of under-served community and private sector
Need to bust myths through a proactive approach
more focussed approach is needed to target social media
Timely sensitisation of press and electronic media

## Slide 15: Action taken from learnings -Revision of IEC
Redesigned IEC and development of additional material
Health workers’ module
Poster for Schools
Advocacy for MR campaign
Handbook on MR campaign for Health Workers and teachers
Leaflets for ASHAs & other FLWs and Religious leaders
Posters, Hoarding and Banner
Posters for private practitioners
Myths & Facts booklet
MR Information Card
MR Vaccination certificate Card

## Slide 16: Measles Rubella campaign phase – 2

## Slide 17
Strong government ownership

## Slide 18: Preparedness for phase 2
High-risk areas identified for preparedness assessment
Operation and communication assessed together using one tool
Daily feedback reporting by monitors
Monitors debriefing to district/State and National task force
Meticulous tracking helped to complete training timely before start of campaign
Intense monitoring to ensure quality of trainings
Conducted
Planned
Notes: More than 39 monitors from national level (from GoI, WHO, UNICEF, ITSU, UNDP, GHS) were deployed for preparedness assessment for phase-2
More than 30 monitors from national level (from GoI, WHO, UNICEF, ITSU, UNDP, GHS) and 10 international monitors (from CDC, SEARO) were deployed for monitoring of campaign

## Slide 19: Improved school strategy
Increased convergence between Health-Education-Women & Child Development at state & district level
Improved engagement with private, public, religious, play schools/creche
Mandatory key education staff training at state/district level
Duration of microplanning increased
Special training material for school teachers, parents & children
WhatsApp/other social media factoids for circulation
Improved engagement with schools

## Slide 20
Focused attention on Parent-Teacher meeting at schools
Interaction of health department with students, especially large private schools
Improving children participation: Drawings, painting competitions

## Slide 21
School children excited for vaccination
Improved communication of health delivery staff & education staff pre, during & post vaccination
(Starts & ends with smiles)
Delighted after Vaccination
A good example of MR vaccination: Video (2:15 -2:45)

## Slide 22
Increased engagement with children – MR Warrior Concept
Engagement with children during observation period for 30 min after MR vaccination

## Slide 23
Involvement of Medical Colleges
Addressing madrasa schools leads
Program tracking meeting at district level
Religious leaders’ meetings
Continued engagement with Lions club
Improved urban strategy for campaign

## Slide 24
Unlike phase 1, support provided for state & district level orientation of leading paediatricians, physicians, clinicians
Intensive support provided by Indian Academy of Paediatricians
  Appeal to endorse & support MR campaign
  Dissemination of FAQs, especially why additional MR dose, safe vaccine messages
  Participation in task forces & awareness through various platforms
  Audio-Visual appeals shared
MR related: IAP endorsement
http://iapindia.org/page.php?id=202
http://iapindia.org/page.php?id=132
Improved convergence with Professional Bodies

## Slide 25: Celebrity involvement
Amitabh Bachchan, Bollywood actor
  Video 1
Dr Devi Shetty, Famous Cardiologist
Factoid videos on MR

## Slide 26
Appeals from Religious leaders
Appeals and endorsement for MR campaign from religious leaders

## Slide 27: Engaging Civil Society & Faith Based Organizations
Engaging community opinion makers

## Slide 28
Chart: HR surge for phase 2
| WHO | UNICEF
Existing human resource | 12 | 14
Additional human resource | 47 | 34
WHO NPSP & UNICEF experts deployed
Selected experienced government/other staff deployed in phase 2 states as rapid response team members
Built capacity of select Govt/WHO/UNICEF/CSOs for next phase
Additional HR deployment

## Slide 29
FAQs on WHO website
FAQs on MoHFW website
FAQs in Urdu
Intensified FAQ dissemination
Samples of FAQ documents

## Slide 30
AEFI committee meeting
AEFI trainings for MO & Health worker
Tagging of session sites to identified AEFI centers
AEFI Kits supplied to each ANM , Supervisor and facility
AEFI communication plan
AEFIs are promptly being managed at session sites
Phase 1: Children were not engaged during observation period for 30 min after MR vaccination
AEFI management in health facilities
Increased emphasis on AEFI management
Phase 2: Engagement with children during observation period for 30 minutes after MR vaccination

## Slide 31
Optimize National, State and District task forces for convergence
  Strengthening inter-departmental coordination
Sufficient preparatory time for SIA
Special attention on School strategy and Urban area planning
Further strengthening Communication and media strategy, including social media management
Engagement of pediatricians & private practitioners
Strengthening supportive supervision
Pre, intra and post-campaign monitoring
Plan post-campaign sweeping based on RCM and administrative coverage data
Phase 2: Interventions
Phase 1: Key lessons learned

## Slide 32
India committed to achieve measles elimination and rubella control by 2020
Sustained efforts are being made to conduct high quality MR campaign
Partner support critical to achieve quality of MR campaign
Reiterating the commitment

## Slide 33
Thank you