## Slide 1: Midterm Review of the Global Measles and Rubella Strategic Plan 2012 – 2020 Summary of the Findings and Implementation Status
Dr Kaushik Banerjee
M&RI Partners' Meeting
Washington DC
7 September 2017

## Slide 2: Objectives of the Review
To provide a candid review of progress toward and key reasons for not attaining, 2015 goals
To assess the quality of implementation of strategies and principles and recommend refinements
To formulate lessons learned and priorities for 2016 – 2020

## Slide 3: Success in reaching 2015 goal and milestones
2015 Goal or Milestone | Evaluation (based on 2015 data)
Achieve > 95% reduction in estimated measles mortality compared to 2000 | Reduction of 79%*
Reduce annual measles incidence to less than 5 cases/million & maintain that level | Global incidence of 36 per million
Achieve at least 90% MCV1 coverage nationally, and > 80% coverage in every district or equivalent administrative unit. | 119 (61%) countries have MCV1 coverage > 90% at national level.
Achieve at least 95% coverage with M, MR or MMR during SIAs in every district. | Of 104 SIAs from 2013-2015, 52 (50%) had a reported coverage of ≥95%. Only 19 conducted a post-SIA coverage survey; 9 (47%) reached ≥95% national coverage
Establish a rubella/CRS elimination goal in at least three additional WHO regions (i.e., in addition to the AMR and EUR that had established goals before 2012). | One additional region, WPR, has established a rubella elimination goal but no date is associated with it
Establish a target date for the global eradication of measles. | No target date for global measles eradication established
Legend
Little or no progress
Some progress but inadequate to meet 2015 goals
* Preliminary data
Notes: Full text of third box under 2015 goal or milestones: Achieve at least 90% MCV1 coverage nationally, and > 80% coverage in every district or equivalent administrative unit with the first routine dose of measles-containing vaccine (or measles- rubella-containing vaccine as appropriate)
2015: 41 countries with SIAs, 20 had coverage >=95%, admin, 4 coverage survey, 1 >=95%
2014: 29 MS, 16 MS (55%) reported >=95% coverage. 2 did coverage surveys, 1>=95%
2013: 34 MS , 16 (47%) reported ≥95% SIA coverage, 13 did coverage surveys, 7 >=95%
104 MS with SIAs, 9/19 did coverage surveys >=95%, 52 (50%) by admin; MS = Member States, this is WHO terminology for countries (or territories) that are members of the WHO.
* The mortality estimates for 2015 are preliminary.

## Slide 4: MTR Overview
Chaired by Professor Walt Orenstein
68 recommendations made in 7 areas:
  Collaboration
  Communications
  Programme performance
  Surveillance
  Outbreaks
  Research
  Resourcing
WHO tracks implementation and reports to SAGE

## Slide 5: Major findings and conclusions (1)
Tremendous progress made towards both measles and rubella elimination since 2001
Significant gains also made during 2012 – 2015
  23/194 WHO Member States introduced MCV2
    Global MCV2 coverage rose from 48% to 61%
  17 countries introduced RCV in their schedule
    Global RCV coverage rose from 39% to 46%
  4.25 million deaths estimated to have been averted during 2012 – 2014 relative to no vaccination
However, neither measles nor rubella elimination on track to achieve the goals
Notes: Per the WHO/IVB database, as of 05 September 2016, 161 countries had introduced MCV2 (and 2 more have plans to introduce during 2016) and 149 countries have rubella containing vaccines (and 9 more have plans to introduce during 2016).

## Slide 6: Major findings and conclusions (2)
The strategies articulated are sound
Implementation has been limited by lack of country ownership and global political will, reflected in insufficient resources
In principle, the 2020 goals can still be reached but doing so would require
  a substantial escalation of political will and resources
  heavy reliance on supplementary immunization activities (SIAs)

## Slide 7: Major findings and conclusions (3)
It is premature to set a timeframe for measles eradication at this point
  A determination should be made, not later than 2020, whether a formal global goal for measles eradication should be set with timeframes for achievement
  In the meantime, all regions should work toward achieving the regional elimination goals

## Slide 8: Increase emphasis on surveillance
Re-orient program to increase emphasis on surveillance so that programmatic and strategic decisions are guided by disease data
Working to achieve measles and rubella elimination can strengthen health systems in general and immunization systems in particular
Strengthening of immunization systems is critical to achieving regional elimination goals.
Disease incidence is the most important indicator of progress

## Slide 9: Surveillance recommendations – status
Develop integrated case-based, lab-supported surveillance and report weekly to WHO
  Status: Monthly reporting at present; weekly reporting very far in future
Implement CRS sentinel or nationwide surveillance
  Status: Ongoing activity, spearheaded by CDC

## Slide 10
Two doses of measles containing vaccine (MCV) or measles-rubella containing vaccine (MRCV) delivered through ongoing services is the standard for all national immunization programs. Preventive SIAs should be conducted on a regular basis, if routine 2 dose coverage is insufficient to achieve and maintain high population immunity
Achieve and Maintain High Levels of Population Immunity
Notes: India’s approach was as follows:
Low RI performing districts are identified based on the large number and percentage of unvaccinated and partially vaccinated children through RI. In each low performing district, communities at high risk are identified using the following criteria:-
Migrant and mobile communities identified under the polio eradication program;
Communities where outbreaks of measles/diphtheria have been reported recently;
Communities served by health centers where the health worker position has been vacant for some time;
Communities where the health worker has not conducted 3 consecutive planned immunization sessions.
Targeted actions are taken as a part of special drives (Mission Indradhanush (Rainbow)) to ensure routine vaccination, including MCV2 coverage, in these areas. Area-specific micro plans are developed, ensuring availability of an adequate number of trained health workers for vaccination, strong mobilization efforts and intensive monitoring in these areas.
Systems are being strengthened for provision of regular routine immunization services in these areas.

## Slide 11: Population Immunity recommendations – status
Monitor and decrease risk through vaccination
  Status: Still needs to be systematically implemented in all countries
Implement 2 dose MCV schedule with SIAs as needed
  Status: New SAGE recommendation to implement 2 doses of MCV in national schedules. SIAs scheduled according to immunity gaps

## Slide 12: Outbreak preparedness and response
Emphasis should be placed on prevention of outbreaks
All measles and rubella outbreaks should be promptly investigated and used to develop a susceptibility profile of the population
Notes: Second bullet: Regions have definitions of outbreaks, but these vary by region. The regional definition varies depending on the level of control in the region.

## Slide 13: Outbreaks recommendations – status
Ensure countries have outbreak preparedness and response plans
  Status: Outbreak investigation and response guidelines in preparation
Use outbreaks to decrease nosocomial transmission
  Status: Standing SAGE recommendation
Respond promptly to outbreaks and create immunity profiles
  Status: In process
Develop protocols on investigating outbreaks and using data for action
  Status: New SOP on outbreaks response in preparation

## Slide 14: Communications – recommendations
Increased resources are needed for communication to raise the visibility of vaccine preventable diseases with a focus on measles and rubella
Creating and promoting demand for immunization requires long term investment

## Slide 15: Communications recommendations – status
Create targeted communications messages
  Status: Pending
Develop rubella messages
  Status: Pending
Address vaccine hesitancy
  Status: Ongoing activity through SAGE WG and Gavi
Conduct research to identify effective messages
  Status: Ongoing activity

## Slide 16: Research and development – recommendations
Programmatically-oriented operations research, in addition to technologically-oriented research, should be used to determine how best to terminate measles transmission including achieving optimal uptake of vaccination in populations, which populations should be targeted for special immunization efforts, how to optimize surveillance systems, and the economic impact of disease

## Slide 17: Research recommendations – status
Review appropriateness of surveillance indicator
  Status: Deferred
Re-evaluate methods to identify target age range for immunization
  Status: In process through SAGE MR WG
Develop country guidance to assess economic burden of outbreaks
  Status: Deferred
Identify positive and negative impact of measles and rubella elimination on routine immunization
  Status: Ongoing activity

## Slide 18: Polio transition – recommendations
Focus on transition of GPEI funded immunization program capacity (including surveillance capacity) is urgent and needs to be a top priority
All stakeholders involved in control and elimination of measles and rubella should engage in polio transition
Strengthening immunization systems and the control and elimination of measles and rubella should be designated as high priorities for polio transition planning and implementation

## Slide 19: Resource Mobilization and Advocacy - recommendations
A multi-year Financial Resource Requirement (FRR) document for measles and rubella vaccination in the context of overall immunization systems should be developed.
The recent welcome additional support from Gavi for measles and rubella activities provides a major step forward for achieving measles and rubella goals. However, it is not, in itself, sufficient to provide adequate assistance globally
Notes: FRR = Financial Resource Requirement

## Slide 20: Resource mobilization – status
Capitalize on polio transition
  Status: WHE resolution; very engaged in transition discussions (TIMB, PPG)
Ensure adequate outbreak response resources
  Status: Stable resources from Gavi; potential increased resources through CDC
Increase communications resources
  Status: Pending
Adequately fund research
  Status: Pending

## Slide 21
Develop multi-year FRR
  Status: Ongoing work, expected completion 12/2017
Ensure adequate M&RI partner resources
  Status: Challenging; forward progress pending FRR
Ensure country co-financing
  Status: Beyond scope of M&RI
Ensure adequate surveillance resources
  Status: Forward progress pending FRR
Resource mobilization – status (2)

## Slide 22: Governance – recommendations
It is imperative that there be close collaboration and coordination between Gavi and the M&RI, as a central element in building the overall immunization system and in order to ensure that measles and rubella control and elimination efforts are coordinated and efficient
Efforts to control and eliminate measles and rubella should be integrated with the general immunization system (including surveillance) and should be used to build and enhance the overall immunization system
Notes: To say orally with reference to the first bullet: Gavi should consider becoming a part of the Management Team of the M&RI.

## Slide 23: Collaboration – status
Establish RVCs in all regions
  Status: RVCs established in 4/6 regions; AFRO and EMRO in development
Develop close collaboration between M&RI and Gavi
  Status: Regular leadership meetings; Big 6 focus agreed upon with country work groups formed; significant progress in Nigeria

## Slide 24: Programme performance – status
Establish NCVs in all countries
  Status: Ongoing activity
Classify cases as preventable or non-preventable
  Status:
Monitor SIA quality and conduct mopping up operations as needed
  Status: Ongoing
Classify countries on elimination status and target strategies appropriately
  Status: To be presented to SAGE in October 2017

## Slide 25: Programme performance – status (2)
Use risk assessment tool at district level
  Status: Standard practice
Identify and destroy reservoirs that are exporting virus
  Status: Pending
Conduct school entry checks in all countries
  Status: Standing SAGE recommendation
Change policies to ensure all susceptibles, regardless of age, are vaccinated
  Status: Encompassed in new platforms such as 2YL and MOV

## Slide 26: Summary
The report recommended:
Focus on improving ongoing immunization systems
Re-orient the measles and rubella elimination programme to increase emphasis on surveillance & outbreak investigation
Measles incidence should be used as an indicator of the health of the immunization and overall health system
Focusing on measles and rubella elimination can result in gains across the immunization system
A costed implementation plan should be developed not later than twelve months after the release of this report
Notes: Bullet 1. This report recommends focusing on improving ongoing immunization systems, although this may delay reaching measles and rubella elimination goals , in order to ensure that gains in measles and rubella control can be sustained
Bullet 2. Re-orienting the measles and rubella elimination program to increase emphasis on surveillance so that programmatic and strategic decisions can be guided by data is critical
Bullet 3. Measles incidence serves as an indicator of the health of the immunization and overall health system
Bullet 4. A focus on measles and rubella elimination can result in gains across the immunization system
Bullet 5. A costed implementation plan in response to these recommendations should be developed not later than twelve months after the release of this report.

## Slide 27: Acknowledgments
MTR team
Walt Orenstein
Alan Hinman
Art Reingold
Benjamin Nkowane
Jean-Marc Olivé
Supported by
Lisa Cairns